## Checkpoints
Step | Checkpoint | Completed By | Date Completed | Value
Survey | Space Available | Moksh Sharma (EMP-000348) | 2026-08-12 | Yes (2026-08-12)
Survey | Power Available | Moksh Sharma (EMP-000348) | 2026-08-12 | Yes (2026-08-12)
Survey | Tile Details | Moksh Sharma (EMP-000348) | 2026-08-12 | test
Survey | Survey Completed | Moksh Sharma (EMP-000348) | 2026-08-12 | Yes (2026-08-12)
Survey | Progress | Moksh Sharma (EMP-000348) | 2026-08-12
SCM / Logistics | Server WH Delivery | Moksh Sharma (EMP-000348) | 2026-08-13
SCM / Logistics | Rack WH Delivery | Moksh Sharma (EMP-000348) | 2026-08-13
SCM / Logistics | PDU WH Delivery | Moksh Sharma (EMP-000348)
SCM / Logistics | Progress | Moksh Sharma (EMP-000348) | 2026-08-12
Onsite Delivery | MO Request | Unassigned | 2026-08-13 | Yes (2026-08-13)
Onsite Delivery | Server On-site Delivery | Unassigned | 2026-08-17
Onsite Delivery | Rack On-site Delivery | Unassigned | 2026-08-17
Onsite Delivery | PDU On-site Delivery | Unassigned
Onsite Delivery | Progress | Unassigned
Material Handover | IM Material | Unassigned | 2026-08-13 | Yes (2026-08-13)
Material Handover | Power-on Material | Unassigned | 2026-08-20 | Yes (2026-08-20)
Material Handover | Material Handover (WH → Site) | Unassigned | 2026-08-13 | Yes (2026-08-13)
Material Handover | Handed Over To | Unassigned | 2026-08-13
Material Handover | Progress | Unassigned
Installation & Configuration | Rack / Server Stacking | Moksh Sharma (EMP-000348) | 2026-08-13 | Yes (2026-08-13)
Installation & Configuration | Power On | Moksh Sharma (EMP-000348) | 2026-08-06 | Yes (2026-08-06)
Installation & Configuration | DAC / ILO Cabling | Moksh Sharma (EMP-000348) | 2026-08-13 | Yes (2026-08-13)
Installation & Configuration | BIOS Configuration | Moksh Sharma (EMP-000348) | 2026-08-13 | Yes (2026-08-13)
Installation & Configuration | Firmware Configuration | Moksh Sharma (EMP-000348) | 2026-08-13 | Yes (2026-08-13)
Installation & Configuration | LLD | Moksh Sharma (EMP-000348) | 2026-08-13 | Yes (2026-08-13)
Installation & Configuration | OS Installation | Moksh Sharma (EMP-000348) | 2026-08-13 | Yes (2026-08-13)
Installation & Configuration | VM Installation | Moksh Sharma (EMP-000348) |  | No
Installation & Configuration | N/W Configuration | Moksh Sharma (EMP-000348) | 2026-08-13 | Yes (2026-08-13)
Installation & Configuration | Tools Integration | Moksh Sharma (EMP-000348) |  | No
Installation & Configuration | MBSS | Moksh Sharma (EMP-000348) | 2026-08-13 | Yes (2026-08-13)
Installation & Configuration | VASCAN | Moksh Sharma (EMP-000348) | 2026-08-13 | Yes (2026-08-13)
Installation & Configuration | Progress | Moksh Sharma (EMP-000348) | 2026-08-12
Acceptance | Handover to Application Team | Moksh Sharma (EMP-000348) | 2026-08-13 | Yes (2026-08-13)
Acceptance | HW-AT Request | Moksh Sharma (EMP-000348) | 2026-08-13 | Yes (2026-08-13)
Acceptance | HW-AT Sign-off | Moksh Sharma (EMP-000348) | 2026-08-13 | Yes (2026-08-13)
Acceptance | Progress | Moksh Sharma (EMP-000348) | 2026-08-12