## Executive Summary
Enterprise ERP Platform — Project Completion
As of 2026-08-05 · Release baseline ERP Core v1.18-beta
Module | Submodules | Avg Backend % | Avg Frontend % | Avg Overall %
Asset Management | 10 | 89 | 38 | 66
BI, Reporting & Analytics | 10 | 81 | 38 | 62
CRM | 10 | 92 | 65 | 80
Compliance & GRC | 12 | 90 | 38 | 66
Customer Portal | 20 | 82 | 41 | 64
Document Management (DMS) | 12 | 87 | 37 | 64
E-Commerce & Channels | 10 | 81 | 37 | 61
Employee Self-Service (ESS) | 6 | 68 | 80 | 73
Finance & Accounting | 11 | 81 | 89 | 85
Foundation | 11 | 92 | 38 | 68
Helpdesk & Support | 10 | 85 | 38 | 64
Human Resources (HR) | 11 | 89 | 77 | 84
Integration Hub | 19 | 78 | 37 | 60
Inventory & Warehouse | 11 | 87 | 37 | 64
Manufacturing | 13 | 81 | 38 | 62
Master Data | 9 | 96 | 38 | 70
Organization | 8 | 80 | 38 | 61
Payroll | 11 | 83 | 39 | 63
Procurement | 9 | 88 | 59 | 75
Project Management | 10 | 87 | 94 | 90
Quality Management | 11 | 86 | 38 | 64
Recruitment | 8 | 85 | 38 | 64
Sales | 9 | 88 | 41 | 67
Service Management | 11 | 78 | 38 | 59
Supply Chain (SCM) | 10 | 75 | 56 | 66
PLATFORM TOTAL (module average) | 272 | 84 | 48 | 68

## Module Detail
Module | Submodule | FRD / Ref | Backend % | Frontend % | Overall % | Status
Asset Management | Asset Allocation | FRD-12 | 82 | 38 | 62 | In progress
Asset Management | Asset Categorization | FRD-12 | 82 | 38 | 62 | In progress
Asset Management | Asset Depreciation | FRD-12 | 96 | 38 | 70 | Substantial
Asset Management | Asset Disposal | FRD-12 | 96 | 38 | 70 | Substantial
Asset Management | Asset Lifecycle Management | FRD-12 | 82 | 38 | 62 | In progress
Asset Management | Asset Maintenance | FRD-12 | 96 | 38 | 70 | Substantial
Asset Management | Asset Registration | FRD-12 | 82 | 38 | 62 | In progress
Asset Management | Asset Return | FRD-12 | 82 | 38 | 62 | In progress
Asset Management | Asset Tracking | FRD-12 | 96 | 38 | 70 | Substantial
Asset Management | Asset Transfer | FRD-12 | 96 | 38 | 70 | Substantial
BI, Reporting & Analytics | Ad Hoc Reporting | FRD-18 | 75 | 38 | 58 | In progress
BI, Reporting & Analytics | Analytics Engine | FRD-18 | 96 | 38 | 70 | Substantial
BI, Reporting & Analytics | Cross Module Reporting | FRD-18 | 75 | 38 | 58 | In progress
BI, Reporting & Analytics | Data Export & BI Integrations | FRD-18 | 86 | 38 | 64 | In progress
BI, Reporting & Analytics | Data Warehouse | FRD-18 | 82 | 30 | 59 | In progress
BI, Reporting & Analytics | Executive Dashboards | FRD-18 | 75 | 48 | 63 | In progress
BI, Reporting & Analytics | Forecasting | FRD-18 | 75 | 30 | 55 | In progress
BI, Reporting & Analytics | KPI Engine | FRD-18 | 96 | 38 | 70 | Substantial
BI, Reporting & Analytics | Operational Dashboards | FRD-18 | 75 | 48 | 63 | In progress
BI, Reporting & Analytics | Scheduled Reporting | FRD-18 | 75 | 38 | 58 | In progress
CRM | Activity Management | FRD-05 | 96 | 66 | 82 | Substantial
CRM | Customer Communication | FRD-05 | 82 | 66 | 75 | Substantial
CRM | Lead Assignment | FRD-05 | 96 | 66 | 82 | Substantial
CRM | Lead Management | FRD-05 | 96 | 66 | 82 | Substantial
CRM | Lead Qualification | FRD-05 | 82 | 66 | 75 | Substantial
CRM | Meeting Management | FRD-05 | 96 | 66 | 82 | Substantial
CRM | Opportunity Management | FRD-05 | 96 | 66 | 82 | Substantial
CRM | Pipeline Management | FRD-05 | 96 | 66 | 82 | Substantial
CRM | Sales Forecasting | FRD-05 | 82 | 58 | 71 | Substantial
CRM | Task Management | FRD-05 | 96 | 66 | 82 | Substantial
Compliance & GRC | Audit Management | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Business Continuity Management (BCM) | FRD-20 | 75 | 38 | 58 | In progress
Compliance & GRC | Compliance Management | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Compliance Register | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Exception Management | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Governance Framework | FRD-20 | 82 | 38 | 62 | In progress
Compliance & GRC | Internal Controls | FRD-20 | 75 | 38 | 58 | In progress
Compliance & GRC | Policy Management | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Regulatory Tracking | FRD-20 | 75 | 38 | 58 | In progress
Compliance & GRC | Risk Assessment | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Risk Management | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Risk Register | FRD-20 | 96 | 38 | 70 | Substantial
Customer Portal | Customer Profiles | ERD-23 | 82 | 38 | 62 | In progress
Customer Portal | Dashboard Widgets | ERD-23 | 82 | 48 | 67 | In progress
Customer Portal | Dashboards | ERD-23 | 75 | 48 | 63 | In progress
Customer Portal | Devices | ERD-23 | 75 | 38 | 58 | In progress
Customer Portal | Document Access | ERD-23 | 96 | 38 | 70 | Substantial
Customer Portal | Download History | ERD-23 | 96 | 38 | 70 | Substantial
Customer Portal | Invoice Views | ERD-23 | 82 | 48 | 67 | In progress
Customer Portal | Login Audit | ERD-23 | 96 | 38 | 70 | Substantial
Customer Portal | Message Threads | ERD-23 | 82 | 38 | 62 | In progress
Customer Portal | Messages | ERD-23 | 75 | 38 | 58 | In progress
Customer Portal | Notifications | ERD-23 | 75 | 38 | 58 | In progress
Customer Portal | Order Views | ERD-23 | 82 | 38 | 62 | In progress
Customer Portal | Portal Accounts | ERD-23 | 82 | 48 | 67 | In progress
Customer Portal | Portal Reports | ERD-23 | 82 | 48 | 67 | In progress
Customer Portal | Portal Sessions | ERD-23 | 82 | 48 | 67 | In progress
Customer Portal | Preferences | ERD-23 | 75 | 38 | 58 | In progress
Customer Portal | Saved Reports | ERD-23 | 82 | 38 | 62 | In progress
Customer Portal | Saved Searches | ERD-23 | 82 | 38 | 62 | In progress
Customer Portal | Service Requests | ERD-23 | 75 | 38 | 58 | In progress
Customer Portal | Support Tickets | ERD-23 | 82 | 38 | 62 | In progress
Document Management (DMS) | Document Approval | FRD-19 | 96 | 38 | 70 | Substantial
Document Management (DMS) | Document Archival | FRD-19 | 82 | 38 | 62 | In progress
Document Management (DMS) | Document Classification | FRD-19 | 82 | 38 | 62 | In progress
Document Management (DMS) | Document Repository | FRD-19 | 96 | 38 | 70 | Substantial
Document Management (DMS) | Document Retention | FRD-19 | 96 | 38 | 70 | Substantial
Document Management (DMS) | Document Search | FRD-19 | 82 | 38 | 62 | In progress
Document Management (DMS) | Document Sharing | FRD-19 | 82 | 38 | 62 | In progress
Document Management (DMS) | Folder Management | FRD-19 | 96 | 38 | 70 | Substantial
Document Management (DMS) | Metadata Management | FRD-19 | 96 | 38 | 70 | Substantial
Document Management (DMS) | OCR Processing | FRD-19 | 75 | 30 | 55 | In progress
Document Management (DMS) | Version Control | FRD-19 | 82 | 38 | 62 | In progress
Document Management (DMS) | e-Signature Integration | FRD-19 | 75 | 30 | 55 | In progress
E-Commerce & Channels | Customer Synchronization | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | External Channel Management | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | Inventory Synchronization | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | Marketplace Integration | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | Mobile App Integration | FRD-22 | 82 | 30 | 59 | In progress
E-Commerce & Channels | Order Synchronization | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | Pricing Synchronization | FRD-22 | 75 | 38 | 58 | In progress
E-Commerce & Channels | Product Synchronization | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | Promotion Synchronization | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | Website Integration | FRD-22 | 75 | 38 | 58 | In progress
Employee Self-Service (ESS) | Announcements | HR-Ext | 68 | 73 | 70 | Substantial
Employee Self-Service (ESS) | Attendance Views | HR-Ext | 68 | 83 | 75 | Substantial
Employee Self-Service (ESS) | Employee Self-Service Portal | HR-Ext | 68 | 83 | 75 | Substantial
Employee Self-Service (ESS) | Leave Requests | HR-Ext | 68 | 83 | 75 | Substantial
Employee Self-Service (ESS) | Payslip Access | HR-Ext | 68 | 83 | 75 | Substantial
Employee Self-Service (ESS) | Profile Updates | HR-Ext | 68 | 73 | 70 | Substantial
Finance & Accounting | Accounts Payable | FRD-04 | 75 | 88 | 81 | Substantial
Finance & Accounting | Accounts Receivable | FRD-04 | 75 | 88 | 81 | Substantial
Finance & Accounting | Bank Reconciliation | FRD-04 | 75 | 88 | 81 | Substantial
Finance & Accounting | Budget Management | FRD-04 | 75 | 88 | 81 | Substantial
Finance & Accounting | Chart of Accounts | FRD-04 | 82 | 95 | 88 | Complete / Beta-ready
Finance & Accounting | Cost Center Accounting | FRD-04 | 82 | 88 | 85 | Complete / Beta-ready
Finance & Accounting | Financial Reporting | FRD-04 | 75 | 88 | 81 | Substantial
Finance & Accounting | General Ledger | FRD-04 | 96 | 88 | 92 | Complete / Beta-ready
Finance & Accounting | Journal Entries | FRD-04 | 82 | 95 | 88 | Complete / Beta-ready
Finance & Accounting | Profit Center Accounting | FRD-04 | 75 | 88 | 81 | Substantial
Finance & Accounting | Tax Engine | FRD-04 | 96 | 88 | 92 | Complete / Beta-ready
Foundation | Audit Engine | FRD-01 | 96 | 38 | 70 | Substantial
Foundation | Authentication | FRD-01 | 75 | 38 | 58 | In progress
Foundation | Notification Engine | FRD-01 | 96 | 38 | 70 | Substantial
Foundation | Organization Context | FRD-01 | 75 | 38 | 58 | In progress
Foundation | Permission Management | FRD-01 | 96 | 38 | 70 | Substantial
Foundation | RBAC Engine | FRD-01 | 96 | 38 | 70 | Substantial
Foundation | Role Management | FRD-01 | 96 | 38 | 70 | Substantial
Foundation | Session Management | FRD-01 | 96 | 38 | 70 | Substantial
Foundation | Settings Management | FRD-01 | 96 | 38 | 70 | Substantial
Foundation | User Management | FRD-01 | 96 | 38 | 70 | Substantial
Foundation | Workflow Engine | FRD-01 | 96 | 38 | 70 | Substantial
Helpdesk & Support | Change Management | FRD-17 | 75 | 38 | 58 | In progress
Helpdesk & Support | Customer Communication | FRD-17 | 82 | 38 | 62 | In progress
Helpdesk & Support | Escalation Management | FRD-17 | 96 | 38 | 70 | Substantial
Helpdesk & Support | Incident Management | FRD-17 | 75 | 38 | 58 | In progress
Helpdesk & Support | Knowledge Base | FRD-17 | 96 | 38 | 70 | Substantial
Helpdesk & Support | Problem Management | FRD-17 | 75 | 38 | 58 | In progress
Helpdesk & Support | SLA Management | FRD-17 | 96 | 38 | 70 | Substantial
Helpdesk & Support | Service Request Management | FRD-17 | 75 | 38 | 58 | In progress
Helpdesk & Support | Support Analytics | FRD-17 | 82 | 38 | 62 | In progress
Helpdesk & Support | Ticket Management | FRD-17 | 96 | 38 | 70 | Substantial
Human Resources (HR) | Attendance Management | FRD-09 | 96 | 83 | 90 | Complete / Beta-ready
Human Resources (HR) | Candidate Management | FRD-09 | 75 | 73 | 74 | Substantial
Human Resources (HR) | Employee Management | FRD-09 | 96 | 83 | 90 | Complete / Beta-ready
Human Resources (HR) | Employee Self Service (ESS) | FRD-09 | 86 | 83 | 85 | Complete / Beta-ready
Human Resources (HR) | Leave Management | FRD-09 | 96 | 83 | 90 | Complete / Beta-ready
Human Resources (HR) | Onboarding | FRD-09 | 75 | 73 | 74 | Substantial
Human Resources (HR) | Performance Management | FRD-09 | 96 | 73 | 86 | Complete / Beta-ready
Human Resources (HR) | Recruitment | FRD-09 | 75 | 73 | 74 | Substantial
Human Resources (HR) | Separation Management | FRD-09 | 96 | 73 | 86 | Complete / Beta-ready
Human Resources (HR) | Shift Management | FRD-09 | 96 | 73 | 86 | Complete / Beta-ready
Human Resources (HR) | Training Management | FRD-09 | 96 | 73 | 86 | Complete / Beta-ready
Integration Hub | API Gateway | FRD-21 | 82 | 38 | 62 | In progress
Integration Hub | Audit Service | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Background Job Processing | FRD-21 | 82 | 38 | 62 | In progress
Integration Hub | Banking Integration | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Email Service | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Event Bus | FRD-21 | 82 | 38 | 62 | In progress
Integration Hub | File Storage Service | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | GST/Tax Integration | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Identity Management (IAM) | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Integration Hub | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Notification Engine | FRD-21 | 96 | 38 | 70 | Substantial
Integration Hub | Payment Gateway Integration | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | SMS Service | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Scheduler Service | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Search Service | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Single Sign-On (SSO) | FRD-21 | 75 | 30 | 55 | In progress
Integration Hub | Webhook Engine | FRD-21 | 96 | 38 | 70 | Substantial
Integration Hub | WhatsApp Service | FRD-21 | 75 | 30 | 55 | In progress
Integration Hub | Workflow Engine | FRD-21 | 75 | 38 | 58 | In progress
Inventory & Warehouse | Barcode Management | FRD-08 | 75 | 30 | 55 | In progress
Inventory & Warehouse | Batch Tracking | FRD-08 | 96 | 38 | 70 | Substantial
Inventory & Warehouse | Bin Management | FRD-08 | 96 | 38 | 70 | Substantial
Inventory & Warehouse | Cycle Counting | FRD-08 | 82 | 38 | 62 | In progress
Inventory & Warehouse | Inventory Management | FRD-08 | 96 | 38 | 70 | Substantial
Inventory & Warehouse | Serial Number Tracking | FRD-08 | 96 | 38 | 70 | Substantial
Inventory & Warehouse | Stock Adjustments | FRD-08 | 82 | 38 | 62 | In progress
Inventory & Warehouse | Stock Movements | FRD-08 | 82 | 38 | 62 | In progress
Inventory & Warehouse | Stock Transfers | FRD-08 | 82 | 38 | 62 | In progress
Inventory & Warehouse | Stock Valuation | FRD-08 | 96 | 38 | 70 | Substantial
Inventory & Warehouse | Warehouse Management | FRD-08 | 75 | 30 | 55 | In progress
Manufacturing | Bill Of Materials (BOM) | FRD-13 | 77 | 38 | 59 | In progress
Manufacturing | Capacity Planning | FRD-13 | 75 | 38 | 58 | In progress
Manufacturing | Finished Goods Receipt | FRD-13 | 77 | 38 | 59 | In progress
Manufacturing | Material Consumption | FRD-13 | 82 | 38 | 62 | In progress
Manufacturing | Material Requirement Planning (MRP) | FRD-13 | 75 | 38 | 58 | In progress
Manufacturing | Production Costing | FRD-13 | 82 | 38 | 62 | In progress
Manufacturing | Production Execution | FRD-13 | 82 | 38 | 62 | In progress
Manufacturing | Production Planning | FRD-13 | 82 | 38 | 62 | In progress
Manufacturing | Rework Management | FRD-13 | 75 | 38 | 58 | In progress
Manufacturing | Routing Management | FRD-13 | 96 | 38 | 70 | Substantial
Manufacturing | Scrap Management | FRD-13 | 96 | 38 | 70 | Substantial
Manufacturing | Shop Floor Control | FRD-13 | 75 | 38 | 58 | In progress
Manufacturing | Work Orders | FRD-13 | 82 | 38 | 62 | In progress
Master Data | Asset Master | FRD-03 | 96 | 38 | 70 | Substantial
Master Data | Currency Master | FRD-03 | 96 | 38 | 70 | Substantial
Master Data | Customer Master | FRD-03 | 96 | 38 | 70 | Substantial
Master Data | Employee Master | FRD-03 | 96 | 48 | 74 | Substantial
Master Data | Product Master | FRD-03 | 96 | 38 | 70 | Substantial
Master Data | Tax Master | FRD-03 | 96 | 38 | 70 | Substantial
Master Data | UOM Master | FRD-03 | 96 | 38 | 70 | Substantial
Master Data | Vendor Master | FRD-03 | 96 | 38 | 70 | Substantial
Master Data | Warehouse Master | FRD-03 | 96 | 30 | 66 | In progress
Organization | Branch Management | FRD-02 | 96 | 38 | 70 | Substantial
Organization | Business Unit Management | FRD-02 | 75 | 38 | 58 | In progress
Organization | Company Management | FRD-02 | 96 | 38 | 70 | Substantial
Organization | Cost Center Management | FRD-02 | 75 | 38 | 58 | In progress
Organization | Department Management | FRD-02 | 75 | 38 | 58 | In progress
Organization | Organization Tree View | FRD-02 | 77 | 38 | 59 | In progress
Organization | Profit Center Management | FRD-02 | 75 | 38 | 58 | In progress
Organization | Tenant Management | FRD-02 | 75 | 38 | 58 | In progress
Payroll | Allowances | FRD-10 | 75 | 38 | 58 | In progress
Payroll | Bank Transfer Processing | FRD-10 | 75 | 38 | 58 | In progress
Payroll | Deductions | FRD-10 | 75 | 38 | 58 | In progress
Payroll | Loans & Advances | FRD-10 | 75 | 38 | 58 | In progress
Payroll | Payroll Accounting | FRD-10 | 96 | 38 | 70 | Substantial
Payroll | Payroll Components | FRD-10 | 82 | 38 | 62 | In progress
Payroll | Payroll Processing | FRD-10 | 96 | 38 | 70 | Substantial
Payroll | Payslip Generation | FRD-10 | 82 | 48 | 67 | In progress
Payroll | Reimbursements | FRD-10 | 75 | 38 | 58 | In progress
Payroll | Salary Structures | FRD-10 | 82 | 38 | 62 | In progress
Payroll | Tax Management | FRD-10 | 96 | 38 | 70 | Substantial
Procurement | Goods Receipt Notes (GRN) | FRD-07 | 75 | 58 | 67 | In progress
Procurement | Purchase Invoicing | FRD-07 | 75 | 58 | 67 | In progress
Procurement | Purchase Orders | FRD-07 | 82 | 58 | 71 | Substantial
Procurement | Purchase Requisition | FRD-07 | 82 | 58 | 71 | Substantial
Procurement | RFQ Management | FRD-07 | 96 | 58 | 79 | Substantial
Procurement | Vendor Comparison | FRD-07 | 96 | 58 | 79 | Substantial
Procurement | Vendor Contracts | FRD-07 | 96 | 58 | 79 | Substantial
Procurement | Vendor Performance | FRD-07 | 96 | 58 | 79 | Substantial
Procurement | Vendor Quotation Management | FRD-07 | 96 | 68 | 83 | Substantial
Project Management | Milestone Management | FRD-11 | 96 | 92 | 94 | Complete / Beta-ready
Project Management | Project Billing | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
Project Management | Project Budgeting | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
Project Management | Project Costing | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
Project Management | Project Management | FRD-11 | 96 | 95 | 96 | Complete / Beta-ready
Project Management | Project Profitability | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
Project Management | Project Reporting | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
Project Management | Resource Allocation | FRD-11 | 96 | 92 | 94 | Complete / Beta-ready
Project Management | Task Management | FRD-11 | 96 | 92 | 94 | Complete / Beta-ready
Project Management | Timesheets | FRD-11 | 75 | 95 | 84 | Substantial
Quality Management | CAPA Management | FRD-14 | 96 | 38 | 70 | Substantial
Quality Management | Compliance Management | FRD-14 | 75 | 38 | 58 | In progress
Quality Management | Customer Quality Complaints | FRD-14 | 86 | 38 | 64 | In progress
Quality Management | Final Quality Inspection | FRD-14 | 96 | 38 | 70 | Substantial
Quality Management | In-Process Quality Inspection | FRD-14 | 96 | 38 | 70 | Substantial
Quality Management | Incoming Quality Inspection | FRD-14 | 96 | 38 | 70 | Substantial
Quality Management | Non-Conformance Management (NCR) | FRD-14 | 77 | 38 | 59 | In progress
Quality Management | Quality Assurance (QA) | FRD-14 | 82 | 38 | 62 | In progress
Quality Management | Quality Audits | FRD-14 | 82 | 38 | 62 | In progress
Quality Management | Quality Control (QC) | FRD-14 | 82 | 38 | 62 | In progress
Quality Management | Quality Planning | FRD-14 | 82 | 38 | 62 | In progress
Recruitment | Applications & Stages | HR-Ext | 75 | 38 | 58 | In progress
Recruitment | Candidate Management | HR-Ext | 96 | 38 | 70 | Substantial
Recruitment | Interviews | HR-Ext | 75 | 38 | 58 | In progress
Recruitment | Job Postings | HR-Ext | 82 | 38 | 62 | In progress
Recruitment | Job Requisitions | HR-Ext | 82 | 38 | 62 | In progress
Recruitment | Offers | HR-Ext | 75 | 38 | 58 | In progress
Recruitment | Onboarding | HR-Ext | 96 | 38 | 70 | Substantial
Recruitment | Talent Pool | HR-Ext | 96 | 38 | 70 | Substantial
Sales | Contract Management | FRD-06 | 75 | 38 | 58 | In progress
Sales | Credit Notes | FRD-06 | 82 | 38 | 62 | In progress
Sales | Invoice Management | FRD-06 | 96 | 48 | 74 | Substantial
Sales | Payment Tracking | FRD-06 | 75 | 38 | 58 | In progress
Sales | Pricing Engine | FRD-06 | 96 | 38 | 70 | Substantial
Sales | Quotation Management | FRD-06 | 96 | 48 | 74 | Substantial
Sales | Returns Management | FRD-06 | 96 | 38 | 70 | Substantial
Sales | Sales Analytics | FRD-06 | 82 | 38 | 62 | In progress
Sales | Sales Order Management | FRD-06 | 96 | 48 | 74 | Substantial
Service Management | Breakdown Maintenance | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Corrective Maintenance | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Field Service Management | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Preventive Maintenance | FRD-16 | 75 | 38 | 58 | In progress
Service Management | SLA Management | FRD-16 | 96 | 38 | 70 | Substantial
Service Management | Service Billing | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Service Contracts | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Service Parts Management | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Service Requests | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Technician Scheduling | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Work Orders | FRD-16 | 82 | 38 | 62 | In progress
Supply Chain (SCM) | Demand Forecasting | FRD-15 | 75 | 50 | 64 | In progress
Supply Chain (SCM) | Demand Planning | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Distribution Planning | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Logistics Management | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Network Planning | FRD-15 | 75 | 50 | 64 | In progress
Supply Chain (SCM) | Shipment Tracking | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Supplier Collaboration | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Supply Chain Analytics | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Supply Planning | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Transportation Management | FRD-15 | 75 | 58 | 67 | In progress

## Legend
How to read this workbook
Submodule names are taken from approved FRD-01–FRD-22 documents plus Portal (ERD-23), Recruitment, and ESS.
Backend % reflects API/services/models signals in apps/api/src/modules (keyword + package presence).
Frontend % reflects Next.js admin UI coverage under apps/web/src/app/(app) (page count + submodule weighting).
Overall % = 55% Backend + 45% Frontend (typical ERP delivery weighting for stakeholder reporting).
Color: Green ≥85% · Amber ≥70% · Peach ≥50% · Red <50%.