## Modules & Submodules
Enterprise ERP Platform — Project Completion
As of 2026-08-06 · Release baseline ERP Core v1.18-beta
Main Module | Submodule | FRD / Ref | Backend % | Frontend % | Overall % | Status
Foundation | Module average (11 submodules) | FRD-01 | 92 | 28 | 63 | In progress
Foundation | Audit Engine | FRD-01 | 96 | 28 | 65 | In progress
| Authentication | FRD-01 | 75 | 28 | 54 | In progress
| Notification Engine | FRD-01 | 96 | 28 | 65 | In progress
| Organization Context | FRD-01 | 75 | 28 | 54 | In progress
| Permission Management | FRD-01 | 96 | 28 | 65 | In progress
| RBAC Engine | FRD-01 | 96 | 28 | 65 | In progress
| Role Management | FRD-01 | 96 | 28 | 65 | In progress
| Session Management | FRD-01 | 96 | 28 | 65 | In progress
| Settings Management | FRD-01 | 96 | 28 | 65 | In progress
| User Management | FRD-01 | 96 | 28 | 65 | In progress
| Workflow Engine | FRD-01 | 96 | 28 | 65 | In progress
Organization | Module average (8 submodules) | FRD-02 | 80 | 28 | 57 | In progress
Organization | Branch Management | FRD-02 | 96 | 28 | 65 | In progress
| Business Unit Management | FRD-02 | 75 | 28 | 54 | In progress
| Company Management | FRD-02 | 96 | 28 | 65 | In progress
| Cost Center Management | FRD-02 | 75 | 28 | 54 | In progress
| Department Management | FRD-02 | 75 | 28 | 54 | In progress
| Organization Tree View | FRD-02 | 77 | 28 | 55 | In progress
| Profit Center Management | FRD-02 | 75 | 28 | 54 | In progress
| Tenant Management | FRD-02 | 75 | 28 | 54 | In progress
Master Data | Module average (9 submodules) | FRD-03 | 96 | 28 | 65 | In progress
Master Data | Asset Master | FRD-03 | 96 | 28 | 65 | In progress
| Currency Master | FRD-03 | 96 | 28 | 65 | In progress
| Customer Master | FRD-03 | 96 | 28 | 65 | In progress
| Employee Master | FRD-03 | 96 | 38 | 70 | Substantial
| Product Master | FRD-03 | 96 | 28 | 65 | In progress
| Tax Master | FRD-03 | 96 | 28 | 65 | In progress
| UOM Master | FRD-03 | 96 | 28 | 65 | In progress
| Vendor Master | FRD-03 | 96 | 28 | 65 | In progress
| Warehouse Master | FRD-03 | 96 | 20 | 62 | In progress
Finance & Accounting | Module average (11 submodules) | FRD-04 | 81 | 89 | 85 | Complete / Beta-ready
Finance & Accounting | Accounts Payable | FRD-04 | 75 | 88 | 81 | Substantial
| Accounts Receivable | FRD-04 | 75 | 88 | 81 | Substantial
| Bank Reconciliation | FRD-04 | 75 | 88 | 81 | Substantial
| Budget Management | FRD-04 | 75 | 88 | 81 | Substantial
| Chart of Accounts | FRD-04 | 82 | 95 | 88 | Complete / Beta-ready
| Cost Center Accounting | FRD-04 | 82 | 88 | 85 | Complete / Beta-ready
| Financial Reporting | FRD-04 | 75 | 88 | 81 | Substantial
| General Ledger | FRD-04 | 96 | 88 | 92 | Complete / Beta-ready
| Journal Entries | FRD-04 | 82 | 95 | 88 | Complete / Beta-ready
| Profit Center Accounting | FRD-04 | 75 | 88 | 81 | Substantial
| Tax Engine | FRD-04 | 96 | 88 | 92 | Complete / Beta-ready
CRM | Module average (10 submodules) | FRD-05 | 92 | 65 | 80 | Substantial
CRM | Activity Management | FRD-05 | 96 | 66 | 82 | Substantial
| Customer Communication | FRD-05 | 82 | 66 | 75 | Substantial
| Lead Assignment | FRD-05 | 96 | 66 | 82 | Substantial
| Lead Management | FRD-05 | 96 | 66 | 82 | Substantial
| Lead Qualification | FRD-05 | 82 | 66 | 75 | Substantial
| Meeting Management | FRD-05 | 96 | 66 | 82 | Substantial
| Opportunity Management | FRD-05 | 96 | 66 | 82 | Substantial
| Pipeline Management | FRD-05 | 96 | 66 | 82 | Substantial
| Sales Forecasting | FRD-05 | 82 | 58 | 71 | Substantial
| Task Management | FRD-05 | 96 | 66 | 82 | Substantial
Sales | Module average (9 submodules) | FRD-06 | 88 | 41 | 67 | In progress
Sales | Contract Management | FRD-06 | 75 | 38 | 58 | In progress
| Credit Notes | FRD-06 | 82 | 38 | 62 | In progress
| Invoice Management | FRD-06 | 96 | 48 | 74 | Substantial
| Payment Tracking | FRD-06 | 75 | 38 | 58 | In progress
| Pricing Engine | FRD-06 | 96 | 38 | 70 | Substantial
| Quotation Management | FRD-06 | 96 | 48 | 74 | Substantial
| Returns Management | FRD-06 | 96 | 38 | 70 | Substantial
| Sales Analytics | FRD-06 | 82 | 38 | 62 | In progress
| Sales Order Management | FRD-06 | 96 | 48 | 74 | Substantial
Procurement | Module average (9 submodules) | FRD-07 | 88 | 59 | 75 | Substantial
Procurement | Goods Receipt Notes (GRN) | FRD-07 | 75 | 58 | 67 | In progress
| Purchase Invoicing | FRD-07 | 75 | 58 | 67 | In progress
| Purchase Orders | FRD-07 | 82 | 58 | 71 | Substantial
| Purchase Requisition | FRD-07 | 82 | 58 | 71 | Substantial
| RFQ Management | FRD-07 | 96 | 58 | 79 | Substantial
| Vendor Comparison | FRD-07 | 96 | 58 | 79 | Substantial
| Vendor Contracts | FRD-07 | 96 | 58 | 79 | Substantial
| Vendor Performance | FRD-07 | 96 | 58 | 79 | Substantial
| Vendor Quotation Management | FRD-07 | 96 | 68 | 83 | Substantial
Inventory & Warehouse | Module average (11 submodules) | FRD-08 | 87 | 37 | 64 | In progress
Inventory & Warehouse | Barcode Management | FRD-08 | 75 | 30 | 55 | In progress
| Batch Tracking | FRD-08 | 96 | 38 | 70 | Substantial
| Bin Management | FRD-08 | 96 | 38 | 70 | Substantial
| Cycle Counting | FRD-08 | 82 | 38 | 62 | In progress
| Inventory Management | FRD-08 | 96 | 38 | 70 | Substantial
| Serial Number Tracking | FRD-08 | 96 | 38 | 70 | Substantial
| Stock Adjustments | FRD-08 | 82 | 38 | 62 | In progress
| Stock Movements | FRD-08 | 82 | 38 | 62 | In progress
| Stock Transfers | FRD-08 | 82 | 38 | 62 | In progress
| Stock Valuation | FRD-08 | 96 | 38 | 70 | Substantial
| Warehouse Management | FRD-08 | 75 | 30 | 55 | In progress
Human Resources (HR) | Module average (11 submodules) | FRD-09 | 89 | 77 | 84 | Substantial
Human Resources (HR) | Attendance Management | FRD-09 | 96 | 83 | 90 | Complete / Beta-ready
| Candidate Management | FRD-09 | 75 | 73 | 74 | Substantial
| Employee Management | FRD-09 | 96 | 83 | 90 | Complete / Beta-ready
| Employee Self Service (ESS) | FRD-09 | 86 | 83 | 85 | Complete / Beta-ready
| Leave Management | FRD-09 | 96 | 83 | 90 | Complete / Beta-ready
| Onboarding | FRD-09 | 75 | 73 | 74 | Substantial
| Performance Management | FRD-09 | 96 | 73 | 86 | Complete / Beta-ready
| Recruitment | FRD-09 | 75 | 73 | 74 | Substantial
| Separation Management | FRD-09 | 96 | 73 | 86 | Complete / Beta-ready
| Shift Management | FRD-09 | 96 | 73 | 86 | Complete / Beta-ready
| Training Management | FRD-09 | 96 | 73 | 86 | Complete / Beta-ready
Payroll | Module average (11 submodules) | FRD-10 | 83 | 39 | 63 | In progress
Payroll | Allowances | FRD-10 | 75 | 38 | 58 | In progress
| Bank Transfer Processing | FRD-10 | 75 | 38 | 58 | In progress
| Deductions | FRD-10 | 75 | 38 | 58 | In progress
| Loans & Advances | FRD-10 | 75 | 38 | 58 | In progress
| Payroll Accounting | FRD-10 | 96 | 38 | 70 | Substantial
| Payroll Components | FRD-10 | 82 | 38 | 62 | In progress
| Payroll Processing | FRD-10 | 96 | 38 | 70 | Substantial
| Payslip Generation | FRD-10 | 82 | 48 | 67 | In progress
| Reimbursements | FRD-10 | 75 | 38 | 58 | In progress
| Salary Structures | FRD-10 | 82 | 38 | 62 | In progress
| Tax Management | FRD-10 | 96 | 38 | 70 | Substantial
Project Management | Module average (10 submodules) | FRD-11 | 87 | 94 | 90 | Complete / Beta-ready
Project Management | Milestone Management | FRD-11 | 96 | 92 | 94 | Complete / Beta-ready
| Project Billing | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
| Project Budgeting | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
| Project Costing | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
| Project Management | FRD-11 | 96 | 95 | 96 | Complete / Beta-ready
| Project Profitability | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
| Project Reporting | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
| Resource Allocation | FRD-11 | 96 | 92 | 94 | Complete / Beta-ready
| Task Management | FRD-11 | 96 | 92 | 94 | Complete / Beta-ready
| Timesheets | FRD-11 | 75 | 95 | 84 | Substantial
Asset Management | Module average (10 submodules) | FRD-12 | 89 | 38 | 66 | In progress
Asset Management | Asset Allocation | FRD-12 | 82 | 38 | 62 | In progress
| Asset Categorization | FRD-12 | 82 | 38 | 62 | In progress
| Asset Depreciation | FRD-12 | 96 | 38 | 70 | Substantial
| Asset Disposal | FRD-12 | 96 | 38 | 70 | Substantial
| Asset Lifecycle Management | FRD-12 | 82 | 38 | 62 | In progress
| Asset Maintenance | FRD-12 | 96 | 38 | 70 | Substantial
| Asset Registration | FRD-12 | 82 | 38 | 62 | In progress
| Asset Return | FRD-12 | 82 | 38 | 62 | In progress
| Asset Tracking | FRD-12 | 96 | 38 | 70 | Substantial
| Asset Transfer | FRD-12 | 96 | 38 | 70 | Substantial
Manufacturing | Module average (13 submodules) | FRD-13 | 81 | 38 | 62 | In progress
Manufacturing | Bill Of Materials (BOM) | FRD-13 | 77 | 38 | 59 | In progress
| Capacity Planning | FRD-13 | 75 | 38 | 58 | In progress
| Finished Goods Receipt | FRD-13 | 77 | 38 | 59 | In progress
| Material Consumption | FRD-13 | 82 | 38 | 62 | In progress
| Material Requirement Planning (MRP) | FRD-13 | 75 | 38 | 58 | In progress
| Production Costing | FRD-13 | 82 | 38 | 62 | In progress
| Production Execution | FRD-13 | 82 | 38 | 62 | In progress
| Production Planning | FRD-13 | 82 | 38 | 62 | In progress
| Rework Management | FRD-13 | 75 | 38 | 58 | In progress
| Routing Management | FRD-13 | 96 | 38 | 70 | Substantial
| Scrap Management | FRD-13 | 96 | 38 | 70 | Substantial
| Shop Floor Control | FRD-13 | 75 | 38 | 58 | In progress
| Work Orders | FRD-13 | 82 | 38 | 62 | In progress
Quality Management | Module average (11 submodules) | FRD-14 | 86 | 38 | 64 | In progress
Quality Management | CAPA Management | FRD-14 | 96 | 38 | 70 | Substantial
| Compliance Management | FRD-14 | 75 | 38 | 58 | In progress
| Customer Quality Complaints | FRD-14 | 86 | 38 | 64 | In progress
| Final Quality Inspection | FRD-14 | 96 | 38 | 70 | Substantial
| In-Process Quality Inspection | FRD-14 | 96 | 38 | 70 | Substantial
| Incoming Quality Inspection | FRD-14 | 96 | 38 | 70 | Substantial
| Non-Conformance Management (NCR) | FRD-14 | 77 | 38 | 59 | In progress
| Quality Assurance (QA) | FRD-14 | 82 | 38 | 62 | In progress
| Quality Audits | FRD-14 | 82 | 38 | 62 | In progress
| Quality Control (QC) | FRD-14 | 82 | 38 | 62 | In progress
| Quality Planning | FRD-14 | 82 | 38 | 62 | In progress
Supply Chain (SCM) | Module average (10 submodules) | FRD-15 | 75 | 56 | 66 | In progress
Supply Chain (SCM) | Demand Forecasting | FRD-15 | 75 | 50 | 64 | In progress
| Demand Planning | FRD-15 | 75 | 58 | 67 | In progress
| Distribution Planning | FRD-15 | 75 | 58 | 67 | In progress
| Logistics Management | FRD-15 | 75 | 58 | 67 | In progress
| Network Planning | FRD-15 | 75 | 50 | 64 | In progress
| Shipment Tracking | FRD-15 | 75 | 58 | 67 | In progress
| Supplier Collaboration | FRD-15 | 75 | 58 | 67 | In progress
| Supply Chain Analytics | FRD-15 | 75 | 58 | 67 | In progress
| Supply Planning | FRD-15 | 75 | 58 | 67 | In progress
| Transportation Management | FRD-15 | 75 | 58 | 67 | In progress
Service Management | Module average (11 submodules) | FRD-16 | 78 | 38 | 59 | In progress
Service Management | Breakdown Maintenance | FRD-16 | 75 | 38 | 58 | In progress
| Corrective Maintenance | FRD-16 | 75 | 38 | 58 | In progress
| Field Service Management | FRD-16 | 75 | 38 | 58 | In progress
| Preventive Maintenance | FRD-16 | 75 | 38 | 58 | In progress
| SLA Management | FRD-16 | 96 | 38 | 70 | Substantial
| Service Billing | FRD-16 | 75 | 38 | 58 | In progress
| Service Contracts | FRD-16 | 75 | 38 | 58 | In progress
| Service Parts Management | FRD-16 | 75 | 38 | 58 | In progress
| Service Requests | FRD-16 | 75 | 38 | 58 | In progress
| Technician Scheduling | FRD-16 | 75 | 38 | 58 | In progress
| Work Orders | FRD-16 | 82 | 38 | 62 | In progress
Helpdesk & Support | Module average (10 submodules) | FRD-17 | 85 | 38 | 64 | In progress
Helpdesk & Support | Change Management | FRD-17 | 75 | 38 | 58 | In progress
| Customer Communication | FRD-17 | 82 | 38 | 62 | In progress
| Escalation Management | FRD-17 | 96 | 38 | 70 | Substantial
| Incident Management | FRD-17 | 75 | 38 | 58 | In progress
| Knowledge Base | FRD-17 | 96 | 38 | 70 | Substantial
| Problem Management | FRD-17 | 75 | 38 | 58 | In progress
| SLA Management | FRD-17 | 96 | 38 | 70 | Substantial
| Service Request Management | FRD-17 | 75 | 38 | 58 | In progress
| Support Analytics | FRD-17 | 82 | 38 | 62 | In progress
| Ticket Management | FRD-17 | 96 | 38 | 70 | Substantial
BI, Reporting & Analytics | Module average (10 submodules) | FRD-18 | 81 | 38 | 62 | In progress
BI, Reporting & Analytics | Ad Hoc Reporting | FRD-18 | 75 | 38 | 58 | In progress
| Analytics Engine | FRD-18 | 96 | 38 | 70 | Substantial
| Cross Module Reporting | FRD-18 | 75 | 38 | 58 | In progress
| Data Export & BI Integrations | FRD-18 | 86 | 38 | 64 | In progress
| Data Warehouse | FRD-18 | 82 | 30 | 59 | In progress
| Executive Dashboards | FRD-18 | 75 | 48 | 63 | In progress
| Forecasting | FRD-18 | 75 | 30 | 55 | In progress
| KPI Engine | FRD-18 | 96 | 38 | 70 | Substantial
| Operational Dashboards | FRD-18 | 75 | 48 | 63 | In progress
| Scheduled Reporting | FRD-18 | 75 | 38 | 58 | In progress
Document Management System (DMS) | Module average (12 submodules) | FRD-19 | 87 | 37 | 64 | In progress
Document Management System (DMS) | Document Approval | FRD-19 | 96 | 38 | 70 | Substantial
| Document Archival | FRD-19 | 82 | 38 | 62 | In progress
| Document Classification | FRD-19 | 82 | 38 | 62 | In progress
| Document Repository | FRD-19 | 96 | 38 | 70 | Substantial
| Document Retention | FRD-19 | 96 | 38 | 70 | Substantial
| Document Search | FRD-19 | 82 | 38 | 62 | In progress
| Document Sharing | FRD-19 | 82 | 38 | 62 | In progress
| Folder Management | FRD-19 | 96 | 38 | 70 | Substantial
| Metadata Management | FRD-19 | 96 | 38 | 70 | Substantial
| OCR Processing | FRD-19 | 75 | 30 | 55 | In progress
| Version Control | FRD-19 | 82 | 38 | 62 | In progress
| e-Signature Integration | FRD-19 | 75 | 30 | 55 | In progress
Compliance & GRC | Module average (12 submodules) | FRD-20 | 90 | 38 | 66 | In progress
Compliance & GRC | Audit Management | FRD-20 | 96 | 38 | 70 | Substantial
| Business Continuity Management (BCM) | FRD-20 | 75 | 38 | 58 | In progress
| Compliance Management | FRD-20 | 96 | 38 | 70 | Substantial
| Compliance Register | FRD-20 | 96 | 38 | 70 | Substantial
| Exception Management | FRD-20 | 96 | 38 | 70 | Substantial
| Governance Framework | FRD-20 | 82 | 38 | 62 | In progress
| Internal Controls | FRD-20 | 75 | 38 | 58 | In progress
| Policy Management | FRD-20 | 96 | 38 | 70 | Substantial
| Regulatory Tracking | FRD-20 | 75 | 38 | 58 | In progress
| Risk Assessment | FRD-20 | 96 | 38 | 70 | Substantial
| Risk Management | FRD-20 | 96 | 38 | 70 | Substantial
| Risk Register | FRD-20 | 96 | 38 | 70 | Substantial
Integration Hub | Module average (19 submodules) | FRD-21 | 78 | 37 | 60 | In progress
Integration Hub | API Gateway | FRD-21 | 82 | 38 | 62 | In progress
| Audit Service | FRD-21 | 75 | 38 | 58 | In progress
| Background Job Processing | FRD-21 | 82 | 38 | 62 | In progress
| Banking Integration | FRD-21 | 75 | 38 | 58 | In progress
| Email Service | FRD-21 | 75 | 38 | 58 | In progress
| Event Bus | FRD-21 | 82 | 38 | 62 | In progress
| File Storage Service | FRD-21 | 75 | 38 | 58 | In progress
| GST/Tax Integration | FRD-21 | 75 | 38 | 58 | In progress
| Identity Management (IAM) | FRD-21 | 75 | 38 | 58 | In progress
| Integration Hub | FRD-21 | 75 | 38 | 58 | In progress
| Notification Engine | FRD-21 | 96 | 38 | 70 | Substantial
| Payment Gateway Integration | FRD-21 | 75 | 38 | 58 | In progress
| SMS Service | FRD-21 | 75 | 38 | 58 | In progress
| Scheduler Service | FRD-21 | 75 | 38 | 58 | In progress
| Search Service | FRD-21 | 75 | 38 | 58 | In progress
| Single Sign-On (SSO) | FRD-21 | 75 | 30 | 55 | In progress
| Webhook Engine | FRD-21 | 96 | 38 | 70 | Substantial
| WhatsApp Service | FRD-21 | 75 | 30 | 55 | In progress
| Workflow Engine | FRD-21 | 75 | 38 | 58 | In progress
E-Commerce & Channels | Module average (10 submodules) | FRD-22 | 81 | 37 | 61 | In progress
E-Commerce & Channels | Customer Synchronization | FRD-22 | 82 | 38 | 62 | In progress
| External Channel Management | FRD-22 | 82 | 38 | 62 | In progress
| Inventory Synchronization | FRD-22 | 82 | 38 | 62 | In progress
| Marketplace Integration | FRD-22 | 82 | 38 | 62 | In progress
| Mobile App Integration | FRD-22 | 82 | 30 | 59 | In progress
| Order Synchronization | FRD-22 | 82 | 38 | 62 | In progress
| Pricing Synchronization | FRD-22 | 75 | 38 | 58 | In progress
| Product Synchronization | FRD-22 | 82 | 38 | 62 | In progress
| Promotion Synchronization | FRD-22 | 82 | 38 | 62 | In progress
| Website Integration | FRD-22 | 75 | 38 | 58 | In progress
Customer Portal | Module average (20 submodules) | ERD-23 | 82 | 41 | 64 | In progress
Customer Portal | Customer Profiles | ERD-23 | 82 | 38 | 62 | In progress
| Dashboard Widgets | ERD-23 | 82 | 48 | 67 | In progress
| Dashboards | ERD-23 | 75 | 48 | 63 | In progress
| Devices | ERD-23 | 75 | 38 | 58 | In progress
| Document Access | ERD-23 | 96 | 38 | 70 | Substantial
| Download History | ERD-23 | 96 | 38 | 70 | Substantial
| Invoice Views | ERD-23 | 82 | 48 | 67 | In progress
| Login Audit | ERD-23 | 96 | 38 | 70 | Substantial
| Message Threads | ERD-23 | 82 | 38 | 62 | In progress
| Messages | ERD-23 | 75 | 38 | 58 | In progress
| Notifications | ERD-23 | 75 | 38 | 58 | In progress
| Order Views | ERD-23 | 82 | 38 | 62 | In progress
| Portal Accounts | ERD-23 | 82 | 48 | 67 | In progress
| Portal Reports | ERD-23 | 82 | 48 | 67 | In progress
| Portal Sessions | ERD-23 | 82 | 48 | 67 | In progress
| Preferences | ERD-23 | 75 | 38 | 58 | In progress
| Saved Reports | ERD-23 | 82 | 38 | 62 | In progress
| Saved Searches | ERD-23 | 82 | 38 | 62 | In progress
| Service Requests | ERD-23 | 75 | 38 | 58 | In progress
| Support Tickets | ERD-23 | 82 | 38 | 62 | In progress
Recruitment | Module average (8 submodules) | HR-Ext | 85 | 38 | 64 | In progress
Recruitment | Applications & Stages | HR-Ext | 75 | 38 | 58 | In progress
| Candidate Management | HR-Ext | 96 | 38 | 70 | Substantial
| Interviews | HR-Ext | 75 | 38 | 58 | In progress
| Job Postings | HR-Ext | 82 | 38 | 62 | In progress
| Job Requisitions | HR-Ext | 82 | 38 | 62 | In progress
| Offers | HR-Ext | 75 | 38 | 58 | In progress
| Onboarding | HR-Ext | 96 | 38 | 70 | Substantial
| Talent Pool | HR-Ext | 96 | 38 | 70 | Substantial
Employee Self-Service (ESS) | Module average (6 submodules) | HR-Ext | 68 | 80 | 73 | Substantial
Employee Self-Service (ESS) | Announcements | HR-Ext | 68 | 73 | 70 | Substantial
| Attendance Views | HR-Ext | 68 | 83 | 75 | Substantial
| Employee Self-Service Portal | HR-Ext | 68 | 83 | 75 | Substantial
| Leave Requests | HR-Ext | 68 | 83 | 75 | Substantial
| Payslip Access | HR-Ext | 68 | 83 | 75 | Substantial
| Profile Updates | HR-Ext | 68 | 73 | 70 | Substantial
Virtual E.A. | Module average (10 submodules) | Roadmap-24 | 27 | 28 | 27 | Planned / Shell UI
Virtual E.A. | Calendar & Meeting Coordination | Roadmap-24 | 33 | 28 | 31 | Planned / Shell UI
| Conversational AI Assistant | Roadmap-24 | 15 | 28 | 21 | Planned / Shell UI
| Email Drafting & Summarization | Roadmap-24 | 30 | 28 | 29 | Planned / Shell UI
| Knowledge Retrieval (RAG) | Roadmap-24 | 33 | 28 | 31 | Planned / Shell UI
| Natural Language ERP Queries | Roadmap-24 | 15 | 28 | 21 | Planned / Shell UI
| Proactive Insights & Alerts | Roadmap-24 | 15 | 28 | 21 | Planned / Shell UI
| Task Automation & Reminders | Roadmap-24 | 33 | 28 | 31 | Planned / Shell UI
| Tenant-Scoped Context & Memory | Roadmap-24 | 27 | 28 | 27 | Planned / Shell UI
| Voice & Chat Interface | Roadmap-24 | 33 | 28 | 31 | Planned / Shell UI
| Workflow & Approval Assistance | Roadmap-24 | 33 | 28 | 31 | Planned / Shell UI
Self Learning Module | Module average (10 submodules) | Roadmap-24 | 77 | 68 | 73 | Substantial
Self Learning Module | Adaptive Learning Recommendations | Roadmap-24 | 75 | 68 | 72 | Substantial
| Certification & Badges | Roadmap-24 | 75 | 68 | 72 | Substantial
| Course Catalog Management | Roadmap-24 | 75 | 68 | 72 | Substantial
| HR Training Integration | Roadmap-24 | 96 | 68 | 83 | Substantial
| Instructor & Admin Console | Roadmap-24 | 75 | 68 | 72 | Substantial
| Learner Progress Dashboards | Roadmap-24 | 75 | 78 | 76 | Substantial
| Learning Paths & Curricula | Roadmap-24 | 75 | 68 | 72 | Substantial
| Lesson & Content Delivery | Roadmap-24 | 75 | 60 | 68 | In progress
| Quizzes & Assessments | Roadmap-24 | 75 | 68 | 72 | Substantial
| Skills Matrix & Competencies | Roadmap-24 | 75 | 68 | 72 | Substantial
Document Management | Module average (10 submodules) | Platform | 79 | 37 | 60 | In progress
Document Management | Access Control & Sharing | Platform | 75 | 38 | 58 | In progress
| Central Document Library | Platform | 77 | 38 | 59 | In progress
| Check-in / Check-out | Platform | 96 | 38 | 70 | Substantial
| Document Approval Workflows | Platform | 86 | 38 | 64 | In progress
| Folder Structure & Taxonomy | Platform | 77 | 38 | 59 | In progress
| Full-Text Search & Discovery | Platform | 75 | 38 | 58 | In progress
| OCR & Metadata Tagging | Platform | 77 | 30 | 56 | In progress
| Retention Policies & Archival | Platform | 77 | 38 | 59 | In progress
| Templates & Standard Forms | Platform | 75 | 38 | 58 | In progress
| Version Control & History | Platform | 77 | 38 | 59 | In progress
Licensing | Module average (10 submodules) | Roadmap-24 | 75 | 28 | 54 | In progress
Licensing | Activation & Validation | Roadmap-24 | 75 | 28 | 54 | In progress
| License Audit & Compliance Reports | Roadmap-24 | 75 | 28 | 54 | In progress
| License Entitlements | Roadmap-24 | 75 | 28 | 54 | In progress
| License Key Generation | Roadmap-24 | 75 | 28 | 54 | In progress
| Multi-Tenant License Isolation | Roadmap-24 | 75 | 28 | 54 | In progress
| Product & Module Licensing | Roadmap-24 | 75 | 28 | 54 | In progress
| Renewal & Expiry Management | Roadmap-24 | 75 | 28 | 54 | In progress
| Seat & User Allocation | Roadmap-24 | 77 | 28 | 55 | In progress
| Subscription Plans & Tiers | Roadmap-24 | 75 | 28 | 54 | In progress
| Usage Metering | Roadmap-24 | 75 | 28 | 54 | In progress
Monitoring & Analytics | Module average (10 submodules) | Platform | 76 | 39 | 59 | In progress
Monitoring & Analytics | API Performance & Latency | Platform | 75 | 38 | 58 | In progress
| Alert Rules & Notifications | Platform | 77 | 38 | 59 | In progress
| Business KPI Dashboards | Platform | 77 | 48 | 64 | In progress
| Custom Report Builder | Platform | 77 | 38 | 59 | In progress
| Error & Exception Tracking | Platform | 82 | 38 | 62 | In progress
| Infrastructure Metrics | Platform | 75 | 38 | 58 | In progress
| Log Aggregation & Search | Platform | 75 | 38 | 58 | In progress
| Real-Time System Health | Platform | 75 | 38 | 58 | In progress
| SLA & Uptime Reporting | Platform | 75 | 38 | 58 | In progress
| User Activity Analytics | Platform | 77 | 38 | 59 | In progress

## Executive Summary
Enterprise ERP Platform — Project Completion
As of 2026-08-06 · Release baseline ERP Core v1.18-beta
Main Module | # Submodules | Submodule Names | Avg Backend % | Avg Frontend % | Avg Overall %
Foundation | 11 | • Audit Engine • Authentication • Notification Engine • Organization Context • Permission Management • RBAC Engine • Role Management • Session Management • Settings Management • User Management • Workflow Engine | 92 | 28 | 63
Organization | 8 | • Branch Management • Business Unit Management • Company Management • Cost Center Management • Department Management • Organization Tree View • Profit Center Management • Tenant Management | 80 | 28 | 57
Master Data | 9 | • Asset Master • Currency Master • Customer Master • Employee Master • Product Master • Tax Master • UOM Master • Vendor Master • Warehouse Master | 96 | 28 | 65
Finance & Accounting | 11 | • Accounts Payable • Accounts Receivable • Bank Reconciliation • Budget Management • Chart of Accounts • Cost Center Accounting • Financial Reporting • General Ledger • Journal Entries • Profit Center Accounting • Tax Engine | 81 | 89 | 85
CRM | 10 | • Activity Management • Customer Communication • Lead Assignment • Lead Management • Lead Qualification • Meeting Management • Opportunity Management • Pipeline Management • Sales Forecasting • Task Management | 92 | 65 | 80
Sales | 9 | • Contract Management • Credit Notes • Invoice Management • Payment Tracking • Pricing Engine • Quotation Management • Returns Management • Sales Analytics • Sales Order Management | 88 | 41 | 67
Procurement | 9 | • Goods Receipt Notes (GRN) • Purchase Invoicing • Purchase Orders • Purchase Requisition • RFQ Management • Vendor Comparison • Vendor Contracts • Vendor Performance • Vendor Quotation Management | 88 | 59 | 75
Inventory & Warehouse | 11 | • Barcode Management • Batch Tracking • Bin Management • Cycle Counting • Inventory Management • Serial Number Tracking • Stock Adjustments • Stock Movements • Stock Transfers • Stock Valuation • Warehouse Management | 87 | 37 | 64
Human Resources (HR) | 11 | • Attendance Management • Candidate Management • Employee Management • Employee Self Service (ESS) • Leave Management • Onboarding • Performance Management • Recruitment • Separation Management • Shift Management • Training Management | 89 | 77 | 84
Payroll | 11 | • Allowances • Bank Transfer Processing • Deductions • Loans & Advances • Payroll Accounting • Payroll Components • Payroll Processing • Payslip Generation • Reimbursements • Salary Structures • Tax Management | 83 | 39 | 63
Project Management | 10 | • Milestone Management • Project Billing • Project Budgeting • Project Costing • Project Management • Project Profitability • Project Reporting • Resource Allocation • Task Management • Timesheets | 87 | 94 | 90
Asset Management | 10 | • Asset Allocation • Asset Categorization • Asset Depreciation • Asset Disposal • Asset Lifecycle Management • Asset Maintenance • Asset Registration • Asset Return • Asset Tracking • Asset Transfer | 89 | 38 | 66
Manufacturing | 13 | • Bill Of Materials (BOM) • Capacity Planning • Finished Goods Receipt • Material Consumption • Material Requirement Planning (MRP) • Production Costing • Production Execution • Production Planning • Rework Management • Routing Management • Scrap Management • Shop Floor Control • Work Orders | 81 | 38 | 62
Quality Management | 11 | • CAPA Management • Compliance Management • Customer Quality Complaints • Final Quality Inspection • In-Process Quality Inspection • Incoming Quality Inspection • Non-Conformance Management (NCR) • Quality Assurance (QA) • Quality Audits • Quality Control (QC) • Quality Planning | 86 | 38 | 64
Supply Chain (SCM) | 10 | • Demand Forecasting • Demand Planning • Distribution Planning • Logistics Management • Network Planning • Shipment Tracking • Supplier Collaboration • Supply Chain Analytics • Supply Planning • Transportation Management | 75 | 56 | 66
Service Management | 11 | • Breakdown Maintenance • Corrective Maintenance • Field Service Management • Preventive Maintenance • SLA Management • Service Billing • Service Contracts • Service Parts Management • Service Requests • Technician Scheduling • Work Orders | 78 | 38 | 59
Helpdesk & Support | 10 | • Change Management • Customer Communication • Escalation Management • Incident Management • Knowledge Base • Problem Management • SLA Management • Service Request Management • Support Analytics • Ticket Management | 85 | 38 | 64
BI, Reporting & Analytics | 10 | • Ad Hoc Reporting • Analytics Engine • Cross Module Reporting • Data Export & BI Integrations • Data Warehouse • Executive Dashboards • Forecasting • KPI Engine • Operational Dashboards • Scheduled Reporting | 81 | 38 | 62
Document Management System (DMS) | 12 | • Document Approval • Document Archival • Document Classification • Document Repository • Document Retention • Document Search • Document Sharing • Folder Management • Metadata Management • OCR Processing • Version Control • e-Signature Integration | 87 | 37 | 64
Compliance & GRC | 12 | • Audit Management • Business Continuity Management (BCM) • Compliance Management • Compliance Register • Exception Management • Governance Framework • Internal Controls • Policy Management • Regulatory Tracking • Risk Assessment • Risk Management • Risk Register | 90 | 38 | 66
Integration Hub | 19 | • API Gateway • Audit Service • Background Job Processing • Banking Integration • Email Service • Event Bus • File Storage Service • GST/Tax Integration • Identity Management (IAM) • Integration Hub • Notification Engine • Payment Gateway Integration • SMS Service • Scheduler Service • Search Service • Single Sign-On (SSO) • Webhook Engine • WhatsApp Service • Workflow Engine | 78 | 37 | 60
E-Commerce & Channels | 10 | • Customer Synchronization • External Channel Management • Inventory Synchronization • Marketplace Integration • Mobile App Integration • Order Synchronization • Pricing Synchronization • Product Synchronization • Promotion Synchronization • Website Integration | 81 | 37 | 61
Customer Portal | 20 | • Customer Profiles • Dashboard Widgets • Dashboards • Devices • Document Access • Download History • Invoice Views • Login Audit • Message Threads • Messages • Notifications • Order Views • Portal Accounts • Portal Reports • Portal Sessions • Preferences • Saved Reports • Saved Searches • Service Requests • Support Tickets | 82 | 41 | 64
Recruitment | 8 | • Applications & Stages • Candidate Management • Interviews • Job Postings • Job Requisitions • Offers • Onboarding • Talent Pool | 85 | 38 | 64
Employee Self-Service (ESS) | 6 | • Announcements • Attendance Views • Employee Self-Service Portal • Leave Requests • Payslip Access • Profile Updates | 68 | 80 | 73
Virtual E.A. | 10 | • Calendar & Meeting Coordination • Conversational AI Assistant • Email Drafting & Summarization • Knowledge Retrieval (RAG) • Natural Language ERP Queries • Proactive Insights & Alerts • Task Automation & Reminders • Tenant-Scoped Context & Memory • Voice & Chat Interface • Workflow & Approval Assistance | 27 | 28 | 27
Self Learning Module | 10 | • Adaptive Learning Recommendations • Certification & Badges • Course Catalog Management • HR Training Integration • Instructor & Admin Console • Learner Progress Dashboards • Learning Paths & Curricula • Lesson & Content Delivery • Quizzes & Assessments • Skills Matrix & Competencies | 77 | 68 | 73
Document Management | 10 | • Access Control & Sharing • Central Document Library • Check-in / Check-out • Document Approval Workflows • Folder Structure & Taxonomy • Full-Text Search & Discovery • OCR & Metadata Tagging • Retention Policies & Archival • Templates & Standard Forms • Version Control & History | 79 | 37 | 60
Licensing | 10 | • Activation & Validation • License Audit & Compliance Reports • License Entitlements • License Key Generation • Multi-Tenant License Isolation • Product & Module Licensing • Renewal & Expiry Management • Seat & User Allocation • Subscription Plans & Tiers • Usage Metering | 75 | 28 | 54
Monitoring & Analytics | 10 | • API Performance & Latency • Alert Rules & Notifications • Business KPI Dashboards • Custom Report Builder • Error & Exception Tracking • Infrastructure Metrics • Log Aggregation & Search • Real-Time System Health • SLA & Uptime Reporting • User Activity Analytics | 76 | 39 | 59
PLATFORM TOTAL (module average) | 322 |  | 81 | 46 | 65

## Module Detail
Main Module | Submodule | FRD / Ref | Backend % | Frontend % | Overall % | Status
Foundation | Module average (11 submodules) | FRD-01 | 92 | 28 | 63 | In progress
Foundation | Audit Engine | FRD-01 | 96 | 28 | 65 | In progress
Foundation | Authentication | FRD-01 | 75 | 28 | 54 | In progress
Foundation | Notification Engine | FRD-01 | 96 | 28 | 65 | In progress
Foundation | Organization Context | FRD-01 | 75 | 28 | 54 | In progress
Foundation | Permission Management | FRD-01 | 96 | 28 | 65 | In progress
Foundation | RBAC Engine | FRD-01 | 96 | 28 | 65 | In progress
Foundation | Role Management | FRD-01 | 96 | 28 | 65 | In progress
Foundation | Session Management | FRD-01 | 96 | 28 | 65 | In progress
Foundation | Settings Management | FRD-01 | 96 | 28 | 65 | In progress
Foundation | User Management | FRD-01 | 96 | 28 | 65 | In progress
Foundation | Workflow Engine | FRD-01 | 96 | 28 | 65 | In progress
Organization | Module average (8 submodules) | FRD-02 | 80 | 28 | 57 | In progress
Organization | Branch Management | FRD-02 | 96 | 28 | 65 | In progress
Organization | Business Unit Management | FRD-02 | 75 | 28 | 54 | In progress
Organization | Company Management | FRD-02 | 96 | 28 | 65 | In progress
Organization | Cost Center Management | FRD-02 | 75 | 28 | 54 | In progress
Organization | Department Management | FRD-02 | 75 | 28 | 54 | In progress
Organization | Organization Tree View | FRD-02 | 77 | 28 | 55 | In progress
Organization | Profit Center Management | FRD-02 | 75 | 28 | 54 | In progress
Organization | Tenant Management | FRD-02 | 75 | 28 | 54 | In progress
Master Data | Module average (9 submodules) | FRD-03 | 96 | 28 | 65 | In progress
Master Data | Asset Master | FRD-03 | 96 | 28 | 65 | In progress
Master Data | Currency Master | FRD-03 | 96 | 28 | 65 | In progress
Master Data | Customer Master | FRD-03 | 96 | 28 | 65 | In progress
Master Data | Employee Master | FRD-03 | 96 | 38 | 70 | Substantial
Master Data | Product Master | FRD-03 | 96 | 28 | 65 | In progress
Master Data | Tax Master | FRD-03 | 96 | 28 | 65 | In progress
Master Data | UOM Master | FRD-03 | 96 | 28 | 65 | In progress
Master Data | Vendor Master | FRD-03 | 96 | 28 | 65 | In progress
Master Data | Warehouse Master | FRD-03 | 96 | 20 | 62 | In progress
Finance & Accounting | Module average (11 submodules) | FRD-04 | 81 | 89 | 85 | Complete / Beta-ready
Finance & Accounting | Accounts Payable | FRD-04 | 75 | 88 | 81 | Substantial
Finance & Accounting | Accounts Receivable | FRD-04 | 75 | 88 | 81 | Substantial
Finance & Accounting | Bank Reconciliation | FRD-04 | 75 | 88 | 81 | Substantial
Finance & Accounting | Budget Management | FRD-04 | 75 | 88 | 81 | Substantial
Finance & Accounting | Chart of Accounts | FRD-04 | 82 | 95 | 88 | Complete / Beta-ready
Finance & Accounting | Cost Center Accounting | FRD-04 | 82 | 88 | 85 | Complete / Beta-ready
Finance & Accounting | Financial Reporting | FRD-04 | 75 | 88 | 81 | Substantial
Finance & Accounting | General Ledger | FRD-04 | 96 | 88 | 92 | Complete / Beta-ready
Finance & Accounting | Journal Entries | FRD-04 | 82 | 95 | 88 | Complete / Beta-ready
Finance & Accounting | Profit Center Accounting | FRD-04 | 75 | 88 | 81 | Substantial
Finance & Accounting | Tax Engine | FRD-04 | 96 | 88 | 92 | Complete / Beta-ready
CRM | Module average (10 submodules) | FRD-05 | 92 | 65 | 80 | Substantial
CRM | Activity Management | FRD-05 | 96 | 66 | 82 | Substantial
CRM | Customer Communication | FRD-05 | 82 | 66 | 75 | Substantial
CRM | Lead Assignment | FRD-05 | 96 | 66 | 82 | Substantial
CRM | Lead Management | FRD-05 | 96 | 66 | 82 | Substantial
CRM | Lead Qualification | FRD-05 | 82 | 66 | 75 | Substantial
CRM | Meeting Management | FRD-05 | 96 | 66 | 82 | Substantial
CRM | Opportunity Management | FRD-05 | 96 | 66 | 82 | Substantial
CRM | Pipeline Management | FRD-05 | 96 | 66 | 82 | Substantial
CRM | Sales Forecasting | FRD-05 | 82 | 58 | 71 | Substantial
CRM | Task Management | FRD-05 | 96 | 66 | 82 | Substantial
Sales | Module average (9 submodules) | FRD-06 | 88 | 41 | 67 | In progress
Sales | Contract Management | FRD-06 | 75 | 38 | 58 | In progress
Sales | Credit Notes | FRD-06 | 82 | 38 | 62 | In progress
Sales | Invoice Management | FRD-06 | 96 | 48 | 74 | Substantial
Sales | Payment Tracking | FRD-06 | 75 | 38 | 58 | In progress
Sales | Pricing Engine | FRD-06 | 96 | 38 | 70 | Substantial
Sales | Quotation Management | FRD-06 | 96 | 48 | 74 | Substantial
Sales | Returns Management | FRD-06 | 96 | 38 | 70 | Substantial
Sales | Sales Analytics | FRD-06 | 82 | 38 | 62 | In progress
Sales | Sales Order Management | FRD-06 | 96 | 48 | 74 | Substantial
Procurement | Module average (9 submodules) | FRD-07 | 88 | 59 | 75 | Substantial
Procurement | Goods Receipt Notes (GRN) | FRD-07 | 75 | 58 | 67 | In progress
Procurement | Purchase Invoicing | FRD-07 | 75 | 58 | 67 | In progress
Procurement | Purchase Orders | FRD-07 | 82 | 58 | 71 | Substantial
Procurement | Purchase Requisition | FRD-07 | 82 | 58 | 71 | Substantial
Procurement | RFQ Management | FRD-07 | 96 | 58 | 79 | Substantial
Procurement | Vendor Comparison | FRD-07 | 96 | 58 | 79 | Substantial
Procurement | Vendor Contracts | FRD-07 | 96 | 58 | 79 | Substantial
Procurement | Vendor Performance | FRD-07 | 96 | 58 | 79 | Substantial
Procurement | Vendor Quotation Management | FRD-07 | 96 | 68 | 83 | Substantial
Inventory & Warehouse | Module average (11 submodules) | FRD-08 | 87 | 37 | 64 | In progress
Inventory & Warehouse | Barcode Management | FRD-08 | 75 | 30 | 55 | In progress
Inventory & Warehouse | Batch Tracking | FRD-08 | 96 | 38 | 70 | Substantial
Inventory & Warehouse | Bin Management | FRD-08 | 96 | 38 | 70 | Substantial
Inventory & Warehouse | Cycle Counting | FRD-08 | 82 | 38 | 62 | In progress
Inventory & Warehouse | Inventory Management | FRD-08 | 96 | 38 | 70 | Substantial
Inventory & Warehouse | Serial Number Tracking | FRD-08 | 96 | 38 | 70 | Substantial
Inventory & Warehouse | Stock Adjustments | FRD-08 | 82 | 38 | 62 | In progress
Inventory & Warehouse | Stock Movements | FRD-08 | 82 | 38 | 62 | In progress
Inventory & Warehouse | Stock Transfers | FRD-08 | 82 | 38 | 62 | In progress
Inventory & Warehouse | Stock Valuation | FRD-08 | 96 | 38 | 70 | Substantial
Inventory & Warehouse | Warehouse Management | FRD-08 | 75 | 30 | 55 | In progress
Human Resources (HR) | Module average (11 submodules) | FRD-09 | 89 | 77 | 84 | Substantial
Human Resources (HR) | Attendance Management | FRD-09 | 96 | 83 | 90 | Complete / Beta-ready
Human Resources (HR) | Candidate Management | FRD-09 | 75 | 73 | 74 | Substantial
Human Resources (HR) | Employee Management | FRD-09 | 96 | 83 | 90 | Complete / Beta-ready
Human Resources (HR) | Employee Self Service (ESS) | FRD-09 | 86 | 83 | 85 | Complete / Beta-ready
Human Resources (HR) | Leave Management | FRD-09 | 96 | 83 | 90 | Complete / Beta-ready
Human Resources (HR) | Onboarding | FRD-09 | 75 | 73 | 74 | Substantial
Human Resources (HR) | Performance Management | FRD-09 | 96 | 73 | 86 | Complete / Beta-ready
Human Resources (HR) | Recruitment | FRD-09 | 75 | 73 | 74 | Substantial
Human Resources (HR) | Separation Management | FRD-09 | 96 | 73 | 86 | Complete / Beta-ready
Human Resources (HR) | Shift Management | FRD-09 | 96 | 73 | 86 | Complete / Beta-ready
Human Resources (HR) | Training Management | FRD-09 | 96 | 73 | 86 | Complete / Beta-ready
Payroll | Module average (11 submodules) | FRD-10 | 83 | 39 | 63 | In progress
Payroll | Allowances | FRD-10 | 75 | 38 | 58 | In progress
Payroll | Bank Transfer Processing | FRD-10 | 75 | 38 | 58 | In progress
Payroll | Deductions | FRD-10 | 75 | 38 | 58 | In progress
Payroll | Loans & Advances | FRD-10 | 75 | 38 | 58 | In progress
Payroll | Payroll Accounting | FRD-10 | 96 | 38 | 70 | Substantial
Payroll | Payroll Components | FRD-10 | 82 | 38 | 62 | In progress
Payroll | Payroll Processing | FRD-10 | 96 | 38 | 70 | Substantial
Payroll | Payslip Generation | FRD-10 | 82 | 48 | 67 | In progress
Payroll | Reimbursements | FRD-10 | 75 | 38 | 58 | In progress
Payroll | Salary Structures | FRD-10 | 82 | 38 | 62 | In progress
Payroll | Tax Management | FRD-10 | 96 | 38 | 70 | Substantial
Project Management | Module average (10 submodules) | FRD-11 | 87 | 94 | 90 | Complete / Beta-ready
Project Management | Milestone Management | FRD-11 | 96 | 92 | 94 | Complete / Beta-ready
Project Management | Project Billing | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
Project Management | Project Budgeting | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
Project Management | Project Costing | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
Project Management | Project Management | FRD-11 | 96 | 95 | 96 | Complete / Beta-ready
Project Management | Project Profitability | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
Project Management | Project Reporting | FRD-11 | 82 | 95 | 88 | Complete / Beta-ready
Project Management | Resource Allocation | FRD-11 | 96 | 92 | 94 | Complete / Beta-ready
Project Management | Task Management | FRD-11 | 96 | 92 | 94 | Complete / Beta-ready
Project Management | Timesheets | FRD-11 | 75 | 95 | 84 | Substantial
Asset Management | Module average (10 submodules) | FRD-12 | 89 | 38 | 66 | In progress
Asset Management | Asset Allocation | FRD-12 | 82 | 38 | 62 | In progress
Asset Management | Asset Categorization | FRD-12 | 82 | 38 | 62 | In progress
Asset Management | Asset Depreciation | FRD-12 | 96 | 38 | 70 | Substantial
Asset Management | Asset Disposal | FRD-12 | 96 | 38 | 70 | Substantial
Asset Management | Asset Lifecycle Management | FRD-12 | 82 | 38 | 62 | In progress
Asset Management | Asset Maintenance | FRD-12 | 96 | 38 | 70 | Substantial
Asset Management | Asset Registration | FRD-12 | 82 | 38 | 62 | In progress
Asset Management | Asset Return | FRD-12 | 82 | 38 | 62 | In progress
Asset Management | Asset Tracking | FRD-12 | 96 | 38 | 70 | Substantial
Asset Management | Asset Transfer | FRD-12 | 96 | 38 | 70 | Substantial
Manufacturing | Module average (13 submodules) | FRD-13 | 81 | 38 | 62 | In progress
Manufacturing | Bill Of Materials (BOM) | FRD-13 | 77 | 38 | 59 | In progress
Manufacturing | Capacity Planning | FRD-13 | 75 | 38 | 58 | In progress
Manufacturing | Finished Goods Receipt | FRD-13 | 77 | 38 | 59 | In progress
Manufacturing | Material Consumption | FRD-13 | 82 | 38 | 62 | In progress
Manufacturing | Material Requirement Planning (MRP) | FRD-13 | 75 | 38 | 58 | In progress
Manufacturing | Production Costing | FRD-13 | 82 | 38 | 62 | In progress
Manufacturing | Production Execution | FRD-13 | 82 | 38 | 62 | In progress
Manufacturing | Production Planning | FRD-13 | 82 | 38 | 62 | In progress
Manufacturing | Rework Management | FRD-13 | 75 | 38 | 58 | In progress
Manufacturing | Routing Management | FRD-13 | 96 | 38 | 70 | Substantial
Manufacturing | Scrap Management | FRD-13 | 96 | 38 | 70 | Substantial
Manufacturing | Shop Floor Control | FRD-13 | 75 | 38 | 58 | In progress
Manufacturing | Work Orders | FRD-13 | 82 | 38 | 62 | In progress
Quality Management | Module average (11 submodules) | FRD-14 | 86 | 38 | 64 | In progress
Quality Management | CAPA Management | FRD-14 | 96 | 38 | 70 | Substantial
Quality Management | Compliance Management | FRD-14 | 75 | 38 | 58 | In progress
Quality Management | Customer Quality Complaints | FRD-14 | 86 | 38 | 64 | In progress
Quality Management | Final Quality Inspection | FRD-14 | 96 | 38 | 70 | Substantial
Quality Management | In-Process Quality Inspection | FRD-14 | 96 | 38 | 70 | Substantial
Quality Management | Incoming Quality Inspection | FRD-14 | 96 | 38 | 70 | Substantial
Quality Management | Non-Conformance Management (NCR) | FRD-14 | 77 | 38 | 59 | In progress
Quality Management | Quality Assurance (QA) | FRD-14 | 82 | 38 | 62 | In progress
Quality Management | Quality Audits | FRD-14 | 82 | 38 | 62 | In progress
Quality Management | Quality Control (QC) | FRD-14 | 82 | 38 | 62 | In progress
Quality Management | Quality Planning | FRD-14 | 82 | 38 | 62 | In progress
Supply Chain (SCM) | Module average (10 submodules) | FRD-15 | 75 | 56 | 66 | In progress
Supply Chain (SCM) | Demand Forecasting | FRD-15 | 75 | 50 | 64 | In progress
Supply Chain (SCM) | Demand Planning | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Distribution Planning | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Logistics Management | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Network Planning | FRD-15 | 75 | 50 | 64 | In progress
Supply Chain (SCM) | Shipment Tracking | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Supplier Collaboration | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Supply Chain Analytics | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Supply Planning | FRD-15 | 75 | 58 | 67 | In progress
Supply Chain (SCM) | Transportation Management | FRD-15 | 75 | 58 | 67 | In progress
Service Management | Module average (11 submodules) | FRD-16 | 78 | 38 | 59 | In progress
Service Management | Breakdown Maintenance | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Corrective Maintenance | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Field Service Management | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Preventive Maintenance | FRD-16 | 75 | 38 | 58 | In progress
Service Management | SLA Management | FRD-16 | 96 | 38 | 70 | Substantial
Service Management | Service Billing | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Service Contracts | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Service Parts Management | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Service Requests | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Technician Scheduling | FRD-16 | 75 | 38 | 58 | In progress
Service Management | Work Orders | FRD-16 | 82 | 38 | 62 | In progress
Helpdesk & Support | Module average (10 submodules) | FRD-17 | 85 | 38 | 64 | In progress
Helpdesk & Support | Change Management | FRD-17 | 75 | 38 | 58 | In progress
Helpdesk & Support | Customer Communication | FRD-17 | 82 | 38 | 62 | In progress
Helpdesk & Support | Escalation Management | FRD-17 | 96 | 38 | 70 | Substantial
Helpdesk & Support | Incident Management | FRD-17 | 75 | 38 | 58 | In progress
Helpdesk & Support | Knowledge Base | FRD-17 | 96 | 38 | 70 | Substantial
Helpdesk & Support | Problem Management | FRD-17 | 75 | 38 | 58 | In progress
Helpdesk & Support | SLA Management | FRD-17 | 96 | 38 | 70 | Substantial
Helpdesk & Support | Service Request Management | FRD-17 | 75 | 38 | 58 | In progress
Helpdesk & Support | Support Analytics | FRD-17 | 82 | 38 | 62 | In progress
Helpdesk & Support | Ticket Management | FRD-17 | 96 | 38 | 70 | Substantial
BI, Reporting & Analytics | Module average (10 submodules) | FRD-18 | 81 | 38 | 62 | In progress
BI, Reporting & Analytics | Ad Hoc Reporting | FRD-18 | 75 | 38 | 58 | In progress
BI, Reporting & Analytics | Analytics Engine | FRD-18 | 96 | 38 | 70 | Substantial
BI, Reporting & Analytics | Cross Module Reporting | FRD-18 | 75 | 38 | 58 | In progress
BI, Reporting & Analytics | Data Export & BI Integrations | FRD-18 | 86 | 38 | 64 | In progress
BI, Reporting & Analytics | Data Warehouse | FRD-18 | 82 | 30 | 59 | In progress
BI, Reporting & Analytics | Executive Dashboards | FRD-18 | 75 | 48 | 63 | In progress
BI, Reporting & Analytics | Forecasting | FRD-18 | 75 | 30 | 55 | In progress
BI, Reporting & Analytics | KPI Engine | FRD-18 | 96 | 38 | 70 | Substantial
BI, Reporting & Analytics | Operational Dashboards | FRD-18 | 75 | 48 | 63 | In progress
BI, Reporting & Analytics | Scheduled Reporting | FRD-18 | 75 | 38 | 58 | In progress
Document Management System (DMS) | Module average (12 submodules) | FRD-19 | 87 | 37 | 64 | In progress
Document Management System (DMS) | Document Approval | FRD-19 | 96 | 38 | 70 | Substantial
Document Management System (DMS) | Document Archival | FRD-19 | 82 | 38 | 62 | In progress
Document Management System (DMS) | Document Classification | FRD-19 | 82 | 38 | 62 | In progress
Document Management System (DMS) | Document Repository | FRD-19 | 96 | 38 | 70 | Substantial
Document Management System (DMS) | Document Retention | FRD-19 | 96 | 38 | 70 | Substantial
Document Management System (DMS) | Document Search | FRD-19 | 82 | 38 | 62 | In progress
Document Management System (DMS) | Document Sharing | FRD-19 | 82 | 38 | 62 | In progress
Document Management System (DMS) | Folder Management | FRD-19 | 96 | 38 | 70 | Substantial
Document Management System (DMS) | Metadata Management | FRD-19 | 96 | 38 | 70 | Substantial
Document Management System (DMS) | OCR Processing | FRD-19 | 75 | 30 | 55 | In progress
Document Management System (DMS) | Version Control | FRD-19 | 82 | 38 | 62 | In progress
Document Management System (DMS) | e-Signature Integration | FRD-19 | 75 | 30 | 55 | In progress
Compliance & GRC | Module average (12 submodules) | FRD-20 | 90 | 38 | 66 | In progress
Compliance & GRC | Audit Management | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Business Continuity Management (BCM) | FRD-20 | 75 | 38 | 58 | In progress
Compliance & GRC | Compliance Management | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Compliance Register | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Exception Management | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Governance Framework | FRD-20 | 82 | 38 | 62 | In progress
Compliance & GRC | Internal Controls | FRD-20 | 75 | 38 | 58 | In progress
Compliance & GRC | Policy Management | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Regulatory Tracking | FRD-20 | 75 | 38 | 58 | In progress
Compliance & GRC | Risk Assessment | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Risk Management | FRD-20 | 96 | 38 | 70 | Substantial
Compliance & GRC | Risk Register | FRD-20 | 96 | 38 | 70 | Substantial
Integration Hub | Module average (19 submodules) | FRD-21 | 78 | 37 | 60 | In progress
Integration Hub | API Gateway | FRD-21 | 82 | 38 | 62 | In progress
Integration Hub | Audit Service | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Background Job Processing | FRD-21 | 82 | 38 | 62 | In progress
Integration Hub | Banking Integration | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Email Service | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Event Bus | FRD-21 | 82 | 38 | 62 | In progress
Integration Hub | File Storage Service | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | GST/Tax Integration | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Identity Management (IAM) | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Integration Hub | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Notification Engine | FRD-21 | 96 | 38 | 70 | Substantial
Integration Hub | Payment Gateway Integration | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | SMS Service | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Scheduler Service | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Search Service | FRD-21 | 75 | 38 | 58 | In progress
Integration Hub | Single Sign-On (SSO) | FRD-21 | 75 | 30 | 55 | In progress
Integration Hub | Webhook Engine | FRD-21 | 96 | 38 | 70 | Substantial
Integration Hub | WhatsApp Service | FRD-21 | 75 | 30 | 55 | In progress
Integration Hub | Workflow Engine | FRD-21 | 75 | 38 | 58 | In progress
E-Commerce & Channels | Module average (10 submodules) | FRD-22 | 81 | 37 | 61 | In progress
E-Commerce & Channels | Customer Synchronization | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | External Channel Management | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | Inventory Synchronization | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | Marketplace Integration | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | Mobile App Integration | FRD-22 | 82 | 30 | 59 | In progress
E-Commerce & Channels | Order Synchronization | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | Pricing Synchronization | FRD-22 | 75 | 38 | 58 | In progress
E-Commerce & Channels | Product Synchronization | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | Promotion Synchronization | FRD-22 | 82 | 38 | 62 | In progress
E-Commerce & Channels | Website Integration | FRD-22 | 75 | 38 | 58 | In progress
Customer Portal | Module average (20 submodules) | ERD-23 | 82 | 41 | 64 | In progress
Customer Portal | Customer Profiles | ERD-23 | 82 | 38 | 62 | In progress
Customer Portal | Dashboard Widgets | ERD-23 | 82 | 48 | 67 | In progress
Customer Portal | Dashboards | ERD-23 | 75 | 48 | 63 | In progress
Customer Portal | Devices | ERD-23 | 75 | 38 | 58 | In progress
Customer Portal | Document Access | ERD-23 | 96 | 38 | 70 | Substantial
Customer Portal | Download History | ERD-23 | 96 | 38 | 70 | Substantial
Customer Portal | Invoice Views | ERD-23 | 82 | 48 | 67 | In progress
Customer Portal | Login Audit | ERD-23 | 96 | 38 | 70 | Substantial
Customer Portal | Message Threads | ERD-23 | 82 | 38 | 62 | In progress
Customer Portal | Messages | ERD-23 | 75 | 38 | 58 | In progress
Customer Portal | Notifications | ERD-23 | 75 | 38 | 58 | In progress
Customer Portal | Order Views | ERD-23 | 82 | 38 | 62 | In progress
Customer Portal | Portal Accounts | ERD-23 | 82 | 48 | 67 | In progress
Customer Portal | Portal Reports | ERD-23 | 82 | 48 | 67 | In progress
Customer Portal | Portal Sessions | ERD-23 | 82 | 48 | 67 | In progress
Customer Portal | Preferences | ERD-23 | 75 | 38 | 58 | In progress
Customer Portal | Saved Reports | ERD-23 | 82 | 38 | 62 | In progress
Customer Portal | Saved Searches | ERD-23 | 82 | 38 | 62 | In progress
Customer Portal | Service Requests | ERD-23 | 75 | 38 | 58 | In progress
Customer Portal | Support Tickets | ERD-23 | 82 | 38 | 62 | In progress
Recruitment | Module average (8 submodules) | HR-Ext | 85 | 38 | 64 | In progress
Recruitment | Applications & Stages | HR-Ext | 75 | 38 | 58 | In progress
Recruitment | Candidate Management | HR-Ext | 96 | 38 | 70 | Substantial
Recruitment | Interviews | HR-Ext | 75 | 38 | 58 | In progress
Recruitment | Job Postings | HR-Ext | 82 | 38 | 62 | In progress
Recruitment | Job Requisitions | HR-Ext | 82 | 38 | 62 | In progress
Recruitment | Offers | HR-Ext | 75 | 38 | 58 | In progress
Recruitment | Onboarding | HR-Ext | 96 | 38 | 70 | Substantial
Recruitment | Talent Pool | HR-Ext | 96 | 38 | 70 | Substantial
Employee Self-Service (ESS) | Module average (6 submodules) | HR-Ext | 68 | 80 | 73 | Substantial
Employee Self-Service (ESS) | Announcements | HR-Ext | 68 | 73 | 70 | Substantial
Employee Self-Service (ESS) | Attendance Views | HR-Ext | 68 | 83 | 75 | Substantial
Employee Self-Service (ESS) | Employee Self-Service Portal | HR-Ext | 68 | 83 | 75 | Substantial
Employee Self-Service (ESS) | Leave Requests | HR-Ext | 68 | 83 | 75 | Substantial
Employee Self-Service (ESS) | Payslip Access | HR-Ext | 68 | 83 | 75 | Substantial
Employee Self-Service (ESS) | Profile Updates | HR-Ext | 68 | 73 | 70 | Substantial
Virtual E.A. | Module average (10 submodules) | Roadmap-24 | 27 | 28 | 27 | Planned / Shell UI
Virtual E.A. | Calendar & Meeting Coordination | Roadmap-24 | 33 | 28 | 31 | Planned / Shell UI
Virtual E.A. | Conversational AI Assistant | Roadmap-24 | 15 | 28 | 21 | Planned / Shell UI
Virtual E.A. | Email Drafting & Summarization | Roadmap-24 | 30 | 28 | 29 | Planned / Shell UI
Virtual E.A. | Knowledge Retrieval (RAG) | Roadmap-24 | 33 | 28 | 31 | Planned / Shell UI
Virtual E.A. | Natural Language ERP Queries | Roadmap-24 | 15 | 28 | 21 | Planned / Shell UI
Virtual E.A. | Proactive Insights & Alerts | Roadmap-24 | 15 | 28 | 21 | Planned / Shell UI
Virtual E.A. | Task Automation & Reminders | Roadmap-24 | 33 | 28 | 31 | Planned / Shell UI
Virtual E.A. | Tenant-Scoped Context & Memory | Roadmap-24 | 27 | 28 | 27 | Planned / Shell UI
Virtual E.A. | Voice & Chat Interface | Roadmap-24 | 33 | 28 | 31 | Planned / Shell UI
Virtual E.A. | Workflow & Approval Assistance | Roadmap-24 | 33 | 28 | 31 | Planned / Shell UI
Self Learning Module | Module average (10 submodules) | Roadmap-24 | 77 | 68 | 73 | Substantial
Self Learning Module | Adaptive Learning Recommendations | Roadmap-24 | 75 | 68 | 72 | Substantial
Self Learning Module | Certification & Badges | Roadmap-24 | 75 | 68 | 72 | Substantial
Self Learning Module | Course Catalog Management | Roadmap-24 | 75 | 68 | 72 | Substantial
Self Learning Module | HR Training Integration | Roadmap-24 | 96 | 68 | 83 | Substantial
Self Learning Module | Instructor & Admin Console | Roadmap-24 | 75 | 68 | 72 | Substantial
Self Learning Module | Learner Progress Dashboards | Roadmap-24 | 75 | 78 | 76 | Substantial
Self Learning Module | Learning Paths & Curricula | Roadmap-24 | 75 | 68 | 72 | Substantial
Self Learning Module | Lesson & Content Delivery | Roadmap-24 | 75 | 60 | 68 | In progress
Self Learning Module | Quizzes & Assessments | Roadmap-24 | 75 | 68 | 72 | Substantial
Self Learning Module | Skills Matrix & Competencies | Roadmap-24 | 75 | 68 | 72 | Substantial
Document Management | Module average (10 submodules) | Platform | 79 | 37 | 60 | In progress
Document Management | Access Control & Sharing | Platform | 75 | 38 | 58 | In progress
Document Management | Central Document Library | Platform | 77 | 38 | 59 | In progress
Document Management | Check-in / Check-out | Platform | 96 | 38 | 70 | Substantial
Document Management | Document Approval Workflows | Platform | 86 | 38 | 64 | In progress
Document Management | Folder Structure & Taxonomy | Platform | 77 | 38 | 59 | In progress
Document Management | Full-Text Search & Discovery | Platform | 75 | 38 | 58 | In progress
Document Management | OCR & Metadata Tagging | Platform | 77 | 30 | 56 | In progress
Document Management | Retention Policies & Archival | Platform | 77 | 38 | 59 | In progress
Document Management | Templates & Standard Forms | Platform | 75 | 38 | 58 | In progress
Document Management | Version Control & History | Platform | 77 | 38 | 59 | In progress
Licensing | Module average (10 submodules) | Roadmap-24 | 75 | 28 | 54 | In progress
Licensing | Activation & Validation | Roadmap-24 | 75 | 28 | 54 | In progress
Licensing | License Audit & Compliance Reports | Roadmap-24 | 75 | 28 | 54 | In progress
Licensing | License Entitlements | Roadmap-24 | 75 | 28 | 54 | In progress
Licensing | License Key Generation | Roadmap-24 | 75 | 28 | 54 | In progress
Licensing | Multi-Tenant License Isolation | Roadmap-24 | 75 | 28 | 54 | In progress
Licensing | Product & Module Licensing | Roadmap-24 | 75 | 28 | 54 | In progress
Licensing | Renewal & Expiry Management | Roadmap-24 | 75 | 28 | 54 | In progress
Licensing | Seat & User Allocation | Roadmap-24 | 77 | 28 | 55 | In progress
Licensing | Subscription Plans & Tiers | Roadmap-24 | 75 | 28 | 54 | In progress
Licensing | Usage Metering | Roadmap-24 | 75 | 28 | 54 | In progress
Monitoring & Analytics | Module average (10 submodules) | Platform | 76 | 39 | 59 | In progress
Monitoring & Analytics | API Performance & Latency | Platform | 75 | 38 | 58 | In progress
Monitoring & Analytics | Alert Rules & Notifications | Platform | 77 | 38 | 59 | In progress
Monitoring & Analytics | Business KPI Dashboards | Platform | 77 | 48 | 64 | In progress
Monitoring & Analytics | Custom Report Builder | Platform | 77 | 38 | 59 | In progress
Monitoring & Analytics | Error & Exception Tracking | Platform | 82 | 38 | 62 | In progress
Monitoring & Analytics | Infrastructure Metrics | Platform | 75 | 38 | 58 | In progress
Monitoring & Analytics | Log Aggregation & Search | Platform | 75 | 38 | 58 | In progress
Monitoring & Analytics | Real-Time System Health | Platform | 75 | 38 | 58 | In progress
Monitoring & Analytics | SLA & Uptime Reporting | Platform | 75 | 38 | 58 | In progress
Monitoring & Analytics | User Activity Analytics | Platform | 77 | 38 | 59 | In progress

## Legend
How to read this workbook
Modules & Submodules: each main module has a bold summary row, then indented submodule rows underneath (column B).
Use Excel outline controls (rows 1–7) to collapse/expand submodule lists per module.
Executive Summary lists every submodule name under each main module in column C.
Submodule names are taken from approved FRD-01–FRD-22, Portal (ERD-23), Recruitment, ESS, and platform extensions (Virtual E.A., Self Learning, Document Management, Licensing, Monitoring & Analytics).
Backend % reflects API/services/models signals in apps/api/src/modules (keyword + package presence).
Frontend % reflects Next.js admin UI coverage under apps/web/src/app/(app) (page count + submodule weighting).
Overall % = 55% Backend + 45% Frontend (typical ERP delivery weighting for stakeholder reporting).
Color: Green ≥85% · Amber ≥70% · Peach ≥50% · Red <50%.